## Feature List (Role-wise)

### 🔐 Common Features (All Users)

- Authentication (Login / OTP / Password)

- Profile management

- Order history

- Notifications (email / SMS / push)

- Invoice & document download (PDF)

## 🧑‍💼 1. Back Office Admin & Staff

### 🔹 Inventory Management

- Product master (battery models, specs, accessories)

- Batch & serial number tracking

- Manufacturing date & expiry tracking

- Stock in / stock out

- Warehouse-wise inventory

- Low stock alerts

### 🔹 Order & Sales Management

- View all orders (wholesaler + consumer)

- Order approval / dispatch

- Invoice generation

- Return & replacement tracking

### 🔹 Warranty Management

- Warranty rules per product

- Warranty activation tracking

- Warranty claim approval / rejection

- Replacement/refund workflow

- Claim history & analytics

### 🔹 Accounts & Finance

- Pricing rules (wholesale vs retail)

- GST / tax management

- Payment reconciliation

- Outstanding payments

- Credit limit for wholesalers

### 🔹 Sales Intelligence (Very Important)

- Region-wise sales

- Dealer/wholesaler performance

- Fast-moving vs slow-moving products

- Warranty claim ratio by product

- Focus areas for sales teams

### 🔹 Admin Controls

- User & role management

- Access control (RBAC)

- System configuration

- Audit logs

## 🏬 2. Wholesaler Portal

### 🔹 Ordering & Inventory

- Place bulk orders

- View pricing slabs

- Track order status

- Maintain own stock

### 🔹 Sales to Consumers

- Register consumer sale

- Assign battery serial number

- Generate warranty certificate for consumer

- Upload sale invoice

### 🔹 Warranty Handling

- Submit warranty claims on behalf of consumer

- Track claim status

- Replacement coordination

### 🔹 Reports

- Sales summary

- Warranty issued

- Warranty claims

- Profit margin view

## 👤 3. Consumer Application

### 🔹 Purchase & Warranty

- Buy battery/accessories (if direct sales)

- Self-register product (serial number + invoice)

- Auto-generate warranty certificate

- View warranty validity

### 🔹 Warranty Claims

- Raise warranty claim

- Upload issue photos/videos

- Track claim progress

### 🔹 Support

- Service center locator

- FAQs & manuals

- Chat / ticket system

High-Level System Architecture

Frontend (Web + Mobile)

|

|

Backend API (Auth, Orders, Inventory, Warranty)

|

|

Database (Relational + Document)

|

|

External Services

- Payment Gateway

- SMS / Email

- PDF generation

Key ideas:

- Single backend serving both web & mobile

- Role-based access control

- Event-based actions (order placed, warranty activated, claim raised)

## Development Plan (Phased – Practical & Safe)

### 🚀 Phase 1: MVP (Core Business)

Focus: Inventory + Orders + Warranty

- Admin inventory management

- Wholesaler ordering

- Consumer warranty registration

- Serial number tracking

- Basic reports

👉 Goal: System usable internally + pilot wholesalers

### 🚀 Phase 2: Business Growth

Focus: Automation & Intelligence

- Analytics dashboards

- Warranty claim workflows

- Notifications

- Payment integration

- Consumer self-service portal

### 🚀 Phase 3: Scale & Optimization

Focus: Performance + Intelligence

- Advanced analytics

- Demand forecasting

- Fraud detection (fake warranty)

- Mobile app optimizations

- Offline support for wholesalers

## Web vs Mobile App Strategy

### Web Application

Best for:

- Admin & staff

- Accounts & analytics

- Wholesaler bulk operations

Modules:

- Admin dashboard

- Inventory

- Reports

- Warranty management

### Mobile Application

Best for:

- Wholesalers in field

- Consumers

Mobile-first features:

- Scan battery QR / serial

- Warranty activation

- Claim submission

- Push notifications

## Suggested Tech Stack (Industry-Proven)

### Backend

- Node.js (NestJS)

- REST APIs

- JWT + Role-based access

### Database

- PostgreSQL (orders, inventory, finance)

- Redis (caching, OTPs)

- S3 / Cloud Storage (invoices, certificates)

### Frontend

- Web: React + Admin UI framework

- Mobile: React Native

### Integrations

- Razorpay / Stripe (payments)

- SMS (Twilio)

- Email (SendGrid)

- PDF generation

## Phase-1 MVP Scope (Scope Locked)

### 🎯 Phase-1 Goal

System must support real battery sales & warranty activation, and be publishable on app stores

### 👇 Included (Must Have)

- Admin web panel

- Wholesaler web + mobile

- Consumer mobile app

- Warranty certificate generation

- Inventory & serial tracking

- Basic reports

- Production deployment

- Play Store + App Store submission assets

### ❌ Excluded (Phase-2 only)

- Advanced analytics

- Credit limits

- Offline-first sync

- Chatbots / AI

- Multi-warehouse optimization

## 3️⃣ Phase-1 Timeline (12 Weeks – Solo Realistic)

### 🔹 WEEK 1 — Product Foundation & Lock Scope

Outcome: You stop changing your mind later

✅ Deliverables:

- Final Phase-1 feature list (1 page)

- User flow diagrams (Admin / Wholesaler / Consumer)

- Warranty lifecycle flow

- Product list (battery models + attributes)

⚠️ Rule:

No new features added after Week 2

### 🔹 WEEK 2 — System Design & Data Modeling

Outcome: No database regret later

✅ Deliverables:

- ER diagram

- API contract (rough)

- Role-permission matrix

- Serial number & warranty logic finalized

📌 Key decision:

- Single backend for web + mobile

- JWT + role-based access

### 🔹 WEEK 3 — Backend Skeleton

Outcome: System backbone ready

✅ Deliverables:

- Project setup

- Auth (Admin / Wholesaler / Consumer)

- Role middleware

- Core models:

  - User

  - Product

  - Inventory

  - SerialNumber

  - Order

  - Warranty

🧠 Tip:

No business logic yet — only CRUD + auth

### 🔹 WEEK 4 — Inventory & Product Module

Outcome: Manufacturer can manage stock

✅ Deliverables:

- Product creation

- Batch & serial upload

- Stock in/out

- Low stock logic

- Admin APIs ready

### 🔹 WEEK 5 — Order Flow (Wholesaler)

Outcome: Money can flow

✅ Deliverables:

- Wholesaler order creation

- Admin order approval

- Order status lifecycle

- Invoice data structure (PDF later)

### 🔹 WEEK 6 — Warranty Core (Critical Week)

Outcome: Core differentiator works

✅ Deliverables:

- Warranty rules per product

- Warranty activation

- Certificate number generation

- Warranty validity tracking

🚨 This week decides project success

### 🔹 WEEK 7 — Admin Web Panel

Outcome: Business operable

✅ Deliverables:

- Admin dashboard

- Inventory screens

- Order management

- Warranty view

- Basic reports

🧩 Use admin UI framework — don’t design from scratch

### 🔹 WEEK 8 — Wholesaler Web + Mobile

Outcome: Real dealer usability

✅ Deliverables:

- Order placement

- Stock view

- Warranty issuance

- Invoice upload

- Mobile barcode/serial scan

### 🔹 WEEK 9 — Consumer Mobile App

Outcome: Customer trust + legitimacy

✅ Deliverables:

- Warranty registration

- Certificate view (PDF)

- Claim raise (basic)

- Notifications

📱 Keep consumer app minimal

### 🔹 WEEK 10 — Infra, Security & Deployment

Outcome: Production-ready

✅ Deliverables:

- Cloud setup (API, DB, storage)

- HTTPS, JWT security

- File storage for invoices & certificates

- Backup strategy

### 🔹 WEEK 11 — App Store & Play Store Prep

Outcome: Business launch ready

✅ Deliverables:

- App icons

- App screenshots

- Store descriptions

- Privacy policy

- Terms & conditions

- App versioning

- TestFlight & Internal testing

📌 Sticker assets included here

### 🔹 WEEK 12 — Testing, Fixes & Launch

Outcome: Go-live

✅ Deliverables:

- Smoke testing

- Bug fixes

- Performance check

- Production deployment

- Store submission

🎉 Phase-1 complete

## App Store / Play Store Sticker Assets (Included)

I will need:

- App icon (1024x1024)

- Feature graphic (Android)

- Screenshots (6–8 per app)

- Splash screen

- Privacy policy URL

💡 Tip: Use Figma + same color palette as brand

## 4️⃣Phase-2 Business Growth

## Timeline (≈ 12 Weeks)

### 🎯 Phase-2 Goal

Reduce operational friction and support real growth without adding people.

### 🔹 Weeks 1–2 — Stabilization & Tech Debt Cleanup

Outcome: Solid foundation for growth

Deliverables:

- Refactor critical flows (orders, warranty)

- Add missing DB indexes

- Improve logging & error handling

- Centralized config & secrets

- API versioning (v1 freeze)

📌 This phase saves you months later — don’t skip.

### 🔹 Weeks 3–4 — Payments & Accounting Automation

Outcome: Money becomes traceable & reliable

Deliverables:

- Payment gateway integration

- Payment status lifecycle

- Invoice auto-generation

- Tax/GST handling

- Outstanding payments tracking

- Credit/debit notes

### 🔹 Weeks 5–6 — Warranty Claims Workflow (Full)

Outcome: Support load goes down

Deliverables:

- Claim approval/rejection flow

- Photo/video uploads

- Replacement vs refund decision logic

- Service-center assignment

- SLA tracking

- Claim history

This is huge for brand trust.

### 🔹 Weeks 7–8 — Notifications & Communication

Outcome: Users stop calling you

Deliverables:

- Email + SMS notifications

- Push notifications

- Event-based triggers

- Template management

- Retry & failure handling

### 🔹 Weeks 9–10 — Analytics & Dashboards (Business View)

Outcome: Data-driven decisions

Deliverables:

- Sales dashboards

- Warranty claim ratios

- Product failure trends

- Dealer performance

- Region-wise sales heatmap

📌 This is where management value starts.

### 🔹 Weeks 11–12 — UX, Performance & Hardening

Outcome: System feels professional

Deliverables:

- UI polish (not redesign)

- Performance tuning

- Caching

- Security audit

- Backup & restore testing

- Load testing (basic)

### ✅ Phase-2 Result

- System is reliable

- Manual work reduced

- Business insights available

- Ready for scale

## 5️⃣Phase-3 Scale & Optimization

## Timeline (≈ 16–20 Weeks)

This phase is optional unless growth demands it.

### 🎯 Phase-3 Goal

Prepare the platform for large scale, multiple regions, and enterprise clients

### 🔹 Weeks 1–3 — Scalability & Performance Engineering

Deliverables:

- Query optimization

- Redis caching strategy

- Background jobs (Celery)

- Async tasks

- CDN setup

- Horizontal scaling readiness

### 🔹 Weeks 4–6 — Advanced Analytics & Reporting

Deliverables:

- Data warehouse setup

- Long-term analytics

- Warranty failure prediction

- Product quality insights

- Exportable reports

This helps manufacturing decisions.

### 🔹 Weeks 7–9 — Dealer & Territory Intelligence

Deliverables:

- Sales target tracking

- Region performance scoring

- Demand forecasting

- Focus area suggestions

- Underperforming dealer detection

This directly helps sales teams.

### 🔹 Weeks 10–12 — Architecture Evolution

Deliverables:

- Modular monolith enforcement

- Extract notification service

- Extract analytics pipeline

- API gateway readiness

- Service boundaries documented

🚨 This is where FastAPI may enter.

### 🔹 Weeks 13–16 — Enterprise Features

Deliverables:

- Multi-company support

- Multi-warehouse

- Role customization

- Audit trails

- Compliance features

- Advanced permissions

### 🔹 (Optional) Weeks 17–20 — Global Readiness

- Multi-language

- Multi-currency

- Region-specific tax

- Timezone handling

### ✅ Phase-3 Result

- Enterprise-ready

- High performance

- Clean evolution path

- Competitive moat